## Sprints Status
Phase | Sprint | Module/Feature | Description | Dependencies | Estimated Effort (Story Points) | Status | Notes | Remarks
Phase 1 | Sprint 1 (Weeks 1-2: Core Setup & User Management) | System Setup | User Login & Role Management | Implement Single Sign-On/Email login, Define roles (Teacher, School Leader, Admin) with permissions, Manage user access (add/edit/delete users, sync with School DB). | None | 8 | Completed | Dataset Dependency for SSO and can be done after AWS. We have added Ekya Nava for testing purposes
Phase 1 | Sprint 1 | Dashboards | Personalized Dashboards | Basic dashboard for Teacher (snapshot of PD Hours, Goals, Feedback), School Leader "Team Overview", Admin settings dashboard. | User Login | 5 | Completed | All Dashboards were created.
Phase 1 | Sprint 1 | Forms Management | Create/Edit Forms | Admin creates/edits observation/goal templates (rubric or free-text), Template library. | User Roles | 5 | Completed | All customised forms were crated and made live in the admin login
Phase 1 | Sprint 2 (Weeks 3-4: Observation & Feedback Basics) | Observations | View & Submit Observation Feedback | Teacher: “My Observations” Tab with feedback cards (date, observer, domain, score), Leader: Open/submit observation forms (multiple templates), Instant notification to teacher. | Dashboards, Forms | 8 | Completed
Phase 1 | Sprint 2 | Goals | Set & Monitor Goals | Goal-setting form (Leader/Teacher), Goal dashboard with progress tracker. | Dashboards | 5 | Completed
Phase 1 | Sprint 2 | Reports | Basic Reports & Trends | Leader: View teacher reports (filter by domain/date/score/trend), Admin: Generate reports across campuses. | Observations, Goals | 5 | Completed | Basic Reports Completed
Phase 1 | Sprint 3 (Weeks 5-6: Training & PD Basics) | Training Calendar | View & Update Training Calendar | Teacher: Calendar with filters (Campus/Topic), register/mark attendance, Leader/Admin: Add/edit events, campus/role visibility. | Dashboards | 5 | In progress | Campus/Topic is pending
Phase 1 | Sprint 3 | Courses | Explore/Enroll in Courses | Teacher: “Courses” tab with filters, self-enroll/nominate, Leader/Admin: Add new courses to catalogue (approval flow). | Training Calendar | 5 | Completed | nominate a person
Phase 1 | Sprint 3 | PD Tracking | Track PD Hours & Insights | Auto-sync PD hours from attendance/courses, Monthly insights (PD Snapshot) via email/dashboard. | Courses, Calendar | 5 | In progress | Email snapshot requires google authentication
Phase 1 | Sprint 4 (Weeks 7-8: Phase 1 Polish & Phase 2 Intro) | Audit & Config | Audit Logs & Platform Config | Admin: Track changes/edits/deletions (activity log), Define observation frequency/approval flows. | Reports | 5 | Completed
Phase 1 | Sprint 4 | Export | Export Reports | Leader/Admin: Select timeframe/campus, auto-generate PDF/Excel. | Reports | 3 | Completed
Phase 2 | Sprint 4 | Teacher Portfolio | Basic Portfolio Dashboard | Teacher: Timeline of activities (goals, observations, trainings, self-learning, assessments, achievements), Add/share key achievements. | Dashboards, Observations, Goals, Courses | 8 | In progress | Key Achivements is pending
Phase 2 | Sprint 5 (Weeks 9-10: Phase 2 Dashboards & Views) | Portfolio Views | HOS/Admin/Dr. Tristha Portfolio Views | HOS/Admin: View each teacher’s portfolio, Dr. Tristha: Similar visibility. | Teacher Portfolio | 5 | In progress
Phase 2 | Sprint 5 | Observations Sub-Module | Teacher View Details | Filled unscheduled/scheduled observations (formal/quick), Scores, observers, average scores, charts over time. | Observations | 5 | In progress | Filtres are missing in tables
Phase 2 | Sprint 5 | Observations Sub-Module | HOS/Coordinator View | Observation targets, observations given, average instructional/learning/cultural tools, Average scores per school/teacher. | Observations | 8 | In progress | Adding option wise explation table or pdf
Phase 2 | Sprint 6 (Weeks 11-12: Phase 2 Advanced Analytics) | Observations Sub-Module | Admin View | Average observations per teacher/campus, scores by campus/observer, target completion %, % tools used. | Observations | 5 | Completed
Phase 2 | Sprint 6 | Observations Sub-Module | Dr. Tristha View | Similar to Admin: Averages per campus/observer, tool usage %. | Observations | 3 | Completed
Phase 2 | Sprint 6 | Portfolio Enhancements | Progress Tracking | Teacher: View goal forms, average observation score, training hours completed/pending, self-paced courses, Progress through year. | Portfolio, Observations, Goals | 5 | Completed
Phase 3 | Sprint 7 (Weeks 13-14: Phase 3 Non-AI Features) | Observation Types | Multiple Observation Types | Walkthrough, formal, self, learning walks, Flexible templates. | Forms, Observations | 8 | Completed
Phase 3 | Sprint 7 | Evidence Attachments | Photo/Doc/Link Attachments | Upload and handle evidence, Privacy controls (private/shared/leadership). | Observations | 5 | In Progress | Privacy controls, Link and Doc formats updation pending
Phase 3 | Sprint 7 | Workflow Enhancements | Teacher Acknowledgement & Ratings | Signature/receipt workflow, Ratings guide and scoring logic. | Observations | 5 | In Progress | Signatures can be only digital mode manner
Phase 3 | Sprint 8 (Weeks 15-16: Phase 3 PD Operations) | PD Calendar | Advanced Calendar Management | Registration, cohorts, capacity, waitlists, Clock hours, certificates, badges, compliance. | Training Calendar | 8 | In Progress | Registrations and duration completed
Phase 3 | Sprint 8 | Course Library | Videos, Quizzes, Reflections | Manage course library, Session feedback surveys. | Courses | 5 | Completed | Only we can add links
Phase 3 | Sprint 8 | Coaching Cycles | Focus, Evidence, Feedback, Action, Follow-up | Log staff meetings/PLCs/1:1s/group coaching. | Observations, Goals | 5 | Completed | Meetings module completed
Phase 3 | Sprint 9 (Weeks 17-18: Phase 3 AI Basics) | AI Transcription and AI observation | Live Mobile Observation (Voice → Text) and AI for checking students presence in classroom | Voice-to-text with tagging/timestamps/offline, Convert spoken feedback. | Observations | 8 | In Progress
Phase 3 | Sprint 9 | AI Tagging | Evidence Tagging to Domains/Standards, Notes interlinking based on teacher and timetable | Auto-tag evidence/uploads to standards (e.g., Danielson). | Evidence Attachments and notes | 5 | Not Started
Phase 3 | Sprint 9 | AI Goal Assistance | AI-Assisted Goal Creation | Suggest measurable SMART goals from notes, Alignment to priorities. | Goals | 5 | Not Started
Phase 3 | Sprint 10 (Weeks 19-20: Phase 3 AI Advanced) | AI Recommendations | PD Recommendation & Skill Gap Mapping | Personalized PD suggestions, Interest groups/communities matching. | Courses, Portfolio | 8 | Not Started
Phase 3 | Sprint 10 | AI Analytics | Session Analytics Dashboard | Interactive dashboards, Predictive growth insights. | Reports, Dashboards | 5 | Completed
Phase 3 | Sprint 10 | AI Coaching | AI Coaching Copilot (Future) | Chat-based AI coach, RAG for knowledge QA. | All Modules | 8 | Not Started
Phase 3 | Sprint 11 (Weeks 21-22: Phase 3 AI Compliance & Polish) | AI Sentiment & Summary | Post-Session Feedback & Reflection Analysis | Analyze surveys/sentiment, Summarize reflections/follow-ups. | PD Calendar, Coaching | 5 | Not Started
Phase 3 | Sprint 11 | AI Scoring | Automated Scoring on Evidence Richness | Predict quality of submissions, Reflection prompt analysis. | Evidence, Goals | 5 | Not Started
Phase 3 | Sprint 11 | Privacy & Compliance | Data Anonymization | PII detection & masking for FERPA/GDPR. | All Data | 3 | Not Started
All Phases | Sprint 12 (Weeks 23-24: Integration & Testing) | Integration | Full System Integration | Connect all modules (e.g., Portfolio pulls from Observations/PD), Cross-role visibility. | All APIs preparation for Integraton | 8 | Not Started
All Phases | Sprint 12 | Search & Filters | Search/Filters by Grade/Subject/Skill | Semantic search across data. | Dashboards, Reports | 5 | Completed
Phase 3 | Sprint 12 | Nudges & Reminders | Smart Reminders & Nudges | Time-series based reminders. | Goals, PD | 5 | Completed
Phase 3 | Sprint 12 | AI Chatbot | Smart Navigdation system |  |  | 8 | Completed

## Wishlist
Wishlist
Multiple observation types (walkthrough, formal, peer, self observation, learning walks)
Live mobile observation mode with quick controls, timestamps, voice to text, offline capture (TBD)
Evidence attachments (photo, document, link) and evidence tagging to domains and standards
Teacher acknowledgement workflow (signature or acknowledgement receipt)
Ratings guide support and scoring logic (levels, weights, evidence requirement rules)
Single teacher timeline that merges observation records, goals, coaching notes, meeting notes, PD, artifacts
Goal setting with alignment to school priorities and automated or assisted goal creation
Coaching cycles (set focus, capture evidence, feedback, action plan, follow up observation, close cycle)
Action plans with tasks, reminders, completion evidence, reflection prompts
Visibility controls (private coach notes, shared notes, leadership view)
Staff meetings, PLCs, 1:1s, grade team meetings, small group coaching sessions logged into the timeline
Interest groups and communities of practice (channels, resources, moderation, goals)
On demand learning and PD operations
Course library (video, readings, quizzes, reflections, assignments)
PD calendar with registration, cohorts, capacity, waitlists, reminders
PD clock hours, certificates, badges, compliance reporting
Session feedback surveys and post session implementation follow up
Search, filters by grade, subject, skill, teacher moves

## Wishlist with Suggestions
Wishlist Item / Feature | Python Libraries / Frameworks | AI Model Type / Example Models (Hugging Face or API) | Purpose / Outcome
Multiple observation types (walkthrough, formal, peer, self, learning walks) | FastAPI, Django, PostgreSQL | Not AI - schema and metadata logic | Define flexible observation templates | P
Live mobile observation (voice → text, timestamps, offline) | transformers, openai-whisper, pydub, librosa | Speech Recognition - Wav2Vec2, Whisper, DistilWhisper | Convert spoken feedback into structured text
Voice-to-text transcription with tagging | spacy, transformers, torch | Wav2Vec2 + spaCy NER for domains | Convert & structure speech data into observations
Evidence attachments (photo, doc, link) | torchvision, transformers | Vision Models - CLIP / BLIP2 | Tag uploaded media to domains & standards | P
Evidence tagging to domains/standards | transformers, sentence-transformers | Text Classification - BERT, RoBERTa, DeBERTa-v3 | Auto-tag evidence to standards (e.g., Danielson)
Teacher acknowledgement workflow (signature or receipt) | Django, FastAPI, docx, PDFKit | Non-AI | Workflow acknowledgment handling | P
Ratings guide support and scoring logic | pandas, numpy, scikit-learn | Rule-based or ML scoring | Automate rating and weighting logic
Single teacher timeline (merge observations, goals, notes, PD) | neo4j, sentence-transformers, langchain | Graph Models + Embeddings | Create unified teacher growth timeline
Goal setting & alignment to priorities | langchain, transformers, openai | Text-to-goal generation - T5, GPT-4, Falcon | Auto-generate SMART goals aligned to school focus
AI-assisted goal creation | langchain, transformers | Generative LLM (GPT / Llama / Mistral) | Suggest measurable goals from observation notes
Coaching cycles (focus, evidence, feedback, action, follow-up) | transformers, langchain, pandas | Summarization + Action Generation - Pegasus, T5, GPT-4 | Auto-generate coaching notes & actions
Action plans (tasks, reminders, reflection prompts) | spacy, textblob, transformers | Task extraction (NER) + Sentiment models | Suggest tasks & generate reflection prompts
Visibility controls (private, shared, leadership view) | django-guardian, fastapi-permissions | Rule-based access logic | Privacy and role-based content visibility
Staff meetings, PLCs, 1:1s, group coaching logged | openai-whisper, transformers | ASR + summarization - Whisper + BART | Auto-generate minutes and insights from discussions
Interest groups & communities of practice | sentence-transformers, lightfm, faiss | Semantic matching + recommender - SBERT / LightFM | Recommend groups, surface relevant resources
On-demand learning & PD operations | sentence-transformers, lightfm, faiss | Recommendation + tagging | Suggest personalized PD courses
Course library (videos, quizzes, reflections) | transformers, torchvision, datasets | NLP + video caption tagging (CLIP / BLIP2 / BART) | Auto-tag courses & generate reflections | P
PD calendar (registration, cohorts, capacity, waitlists) | Django, FastAPI, Celery | No AI - scheduling logic | Event registration management | P
PD clock hours, certificates, badges, compliance | pandas, pdfkit, qrcode | Rule engine | Automate PD tracking and certification
Session feedback surveys & sentiment | vaderSentiment, bertopic, transformers | Sentiment + Topic Modeling - BERT, VADER, BERTopic | Analyze feedback and extract key insights | P
Post-session implementation follow-up | transformers, langchain | Text Summarization - Pegasus / GPT | Summarize reflections and follow-up notes | P
Search, filters by grade, subject, skill, teacher moves | faiss, chromadb, sentence-transformers | Vector Search + Semantic Retrieval | Semantic filtering and retrieval across data | P
PD clock hours & compliance reporting | pandas, xgboost, dash | Predictive analytics + logs | Generate progress and compliance summaries
AI goal recommendation based on performance | langchain, transformers, openai | Generative LLM (GPT-4 / Mistral / Falcon) | Suggest next goals using historical data
Reflection prompt analysis | vaderSentiment, t5, textblob | Sentiment + Summary | Evaluate reflective writing quality
Automated scoring based on evidence richness | xgboost, sklearn | Regression model (Linear / XGBoost) | Predict quality of evidence submissions
PD recommendation & skill gap mapping | lightfm, faiss, sentence-transformers | Hybrid recommender (collaborative + content) | Personalized PD suggestions
Smart reminders & nudges | prophet, celery, xgboost | Time-series + trigger ML | Send smart follow-up reminders
Session analytics dashboard | plotly, dash, streamlit, matplotlib | Data visualization | Interactive insight dashboards
AI coaching copilot (future) | langchain, transformers, chromadb, faiss | Chat-based LLM - Llama-3, GPT-4, Mistral-7B-Instruct | Interactive AI coach for teachers/admins
RAG pipeline for knowledge QA | langchain, faiss, chromadb | Retriever + Generator - SBERT + GPT-4 | Contextualized answers for PD and coaching
Predictive growth and coaching insights | xgboost, torch, prophet | Regression / Neural Time-Series | Forecast teacher progress and PD impact
Data anonymization (privacy compliance) | presidio-analyzer, re, spacy | PII detection & masking | FERPA/GDPR-safe data handling

## Libraries
Category | Libraries
NLP & Transformers | transformers, sentence-transformers, datasets, tokenizers
Speech / Audio | transformers, librosa, soundfile, (optional Whisper libs)
ML & Prediction | scikit-learn, xgboost, prophet, lightfm
Search & Embeddings | faiss, chromadb
Backend & API | FastAPI, Django, Celery, Redis
Visualization & Dashboards | Plotly, Dash, Streamlit

## AI Models
Category | Application | Example Models (Hugging Face)
ASR (Speech) | Live observation transcription | facebook/wav2vec2-large-960h, openai/whisper-large-v3
Text Classification / Tagging | Evidence tagging, domain classification | roberta-base, distilbert-base-uncased, facebook/bart-large-mnli
Summarization | Observation + PD feedback summaries | google/pegasus-xsum, facebook/bart-large-cnn, allenai/led-base-16384
Embeddings / Semantic Search | Semantic tagging, recommendations | sentence-transformers/all-MiniLM-L6-v2, multi-qa-mpnet-base-dot-v1
Vision + Text (CLIP) | Evidence photo/doc tagging | openai/clip-vit-base-patch32, Salesforce/blip2
Sentiment / Topic Modeling | Reflection & feedback analysis | nlptown/bert-base-multilingual-uncased-sentiment, vaderSentiment, bertopic
Recommenders | PD & interest group suggestions | Not HF (use LightFM, hybrid with embeddings)
Generative (LLMs) | Goal writing, coaching copilot | meta-llama/Llama-3, mistralai/Mixtral, tiiuae/falcon-40b-instruct
Time-Series / Forecasting | Reminders, growth prediction | Prophet / XGBoost / LSTM

## Sprint Wise Table
Sprint-wise Plan Table
Sprint Name | Modules Covered | Feature Details | Tasks Finished
Sprint 0 – Foundation & Setup | Core Infrastructure, Authentication (Base), DevOps | Monorepo setup, CI/CD pipeline, DB schema, basic auth, layout skeleton | Repo setup, CI/CD configured, Prisma schema created, basic login, Docker local setup
Sprint 1 – Authentication & Dashboards (P1) | Authentication & User Management, Dashboard | SSO/email login, RBAC, role-based dashboards, real-time widget skeleton | NextAuth integrated, roles defined, dashboard UI built, Socket.io base connection
Sprint 2 – Observations & Feedback Core (P1) | Observations & Feedback | Observation forms, feedback submission, real-time notifications, feedback cards | Observation form stub, feedback APIs, UI cards, notification system
Sprint 3 – Training Calendar & Config (P1) | Training Calendar, Form Builder (Basic), Admin Config | Calendar view & registration, event CRUD, basic form templates | Calendar UI, event management, registration flow, basic forms created
Sprint 4 – Goals & Reflections (P2) | Goals Module, Feedback (Reflections) | Goal creation, progress tracking, teacher reflections on feedback | Goal workflows, progress visuals, reflection UI, notifications
Sprint 5 – Reports & Analytics (P2) | Reports & Analytics | Reports, trends, filters, exports (PDF/Excel) | Charts implemented, reporting logic, export functionality
Sprint 6 – Courses & PD Hours (P3) | Courses Module, PD Hours Tracking | Course catalogue, enrollment, PD hours auto-calculation | Course builder, enrollment flow, hours calculation engine
Sprint 7 – Advanced Admin Tools (P2–P3) | Admin Tools, Form Builder (Advanced) | User management, audit logs, advanced form builder | Bulk user import, audit logs UI, drag-drop form builder
Sprint 8 – Insights & Launch Prep (P4) | Insights Module, System Polish | Monthly insights, optional AI recommendations, performance & security hardening | Insights automation, bug fixes, accessibility audit, E2E testing, launch readiness

## PDI Sprints Details
Sprint 0: Foundation & Setup (1 Week Prep)
Sprint 1: Core Authentication & Dashboards (P1) | Modules: Authentication & User Management, Dashboard Module.
Sprint 2: Observations & Feedback Core (P1) | Modules:Observations & Feedback Module.
Sprint 3: Training Calendar & Basic Configuration (P1 Completion) | Modules: Training Calendar Module, Form Builder & Configuration (basic).
Sprint 4: Goals & Reflections (P2) | Modules: Goals Module, Observations & Feedback (reflections).
Sprint 5: Reports & Exports (P2) | Modules: Reports & Analytics Module.
Sprint 6: Courses & PD Hours (P3) | Modules: Courses & PD Hours Module.
Sprint 7: Advanced Admin Tools & Configuration (P2–P3) | Modules: Admin Tools, Form Builder (advanced).
Sprint 8: Insights, Polish & Launch Prep (P4 + Refinements) | Modules: Insights Module, overall polish.

## Product Check
PRODUCT FEATURE FINAL CHECKLIST
S.No | Checklist Item | Status (Yes / No / Partial)
1 | User Roles defined (Admin / Leader / Teacher / Viewer etc.)
2 | Role-based access & permissions working correctly
3 | Login & authentication flow complete
4 | Forgot password / reset password working
5 | User onboarding / first-time setup flow available
6 | Dashboard available for each role
7 | Dashboard shows real-time / correct data
8 | Navigation between modules smooth & consistent
9 | Global search available (if required)
10 | Filters & sorting working across modules
11 | Data validation rules applied
12 | Mandatory fields enforced
13 | Error messages shown clearly
14 | Success / confirmation messages shown
15 | Audit logs / activity logs captured
16 | Export options available (Excel / PDF)
17 | Notifications (email / in-app) implemented
18 | Performance acceptable with real data
19 | Mobile / tablet responsiveness checked
20 | Security basics covered (access, data isolation)
MODULE-WISE FEATURE CHECKLIST
S.No | Checklist Item | Status
21 | Module creation framework finalized
22 | CRUD operations (Create / View / Edit / Delete) working
23 | Bulk upload / import available (if applicable)
24 | Data relationships between modules mapped correctly
25 | Historical data retained (no overwrite issues)
26 | Reports / analytics available for module
27 | Trends / comparison views implemented
28 | Role-wise visibility inside module
29 | Approval workflows (if any) implemented
30 | Module settings / configurations available
DATA & TRENDS / REPORTING CHECKLIST
S.No | Checklist Item | Status
31 | Data source mapping completed
32 | Real-time vs static data clearly defined
33 | Trend charts accurate & readable
34 | Filters (date, campus, role etc.) working
35 | Drill-down from summary to detail view
36 | Download / export of reports available
37 | Data refresh logic documented
38 | Edge cases handled (no data, partial data)
ADMIN & CONFIGURATION CHECKLIST
S.No | Checklist Item | Status
39 | Admin can manage users & roles
40 | Admin can enable / disable modules
41 | Admin configuration changes reflect immediately
42 | Master data management screens available
43 | System settings documented
FINAL GO-LIVE CHECKLIST
S.No | Checklist Item | Status
44 | UAT completed with stakeholders
45 | Known issues documented
46 | Critical bugs resolved
47 | User manual / SOP available
48 | Demo / walkthrough done for users
49 | Production deployment tested
50 | Go-Live approval received

## Module Wise Check
MODULE 1: DATA & TRENDS — TRAININGS
S.No | Module | Sub-Module | Feature | Admin | Leader | Teacher | Data Source | Logic | Status | Risk | Remarks
1 | Data & Trends | Trainings | List of completed trainings | Yes | Yes | Yes | PDI | Static
2 | Data & Trends | Trainings | Upcoming trainings visibility | Yes | Yes | Yes | PDI | Static
3 | Data & Trends | Trainings | Attendance tracking | Yes | Yes | No | PDI | Aggregated
4 | Data & Trends | Trainings | Completion % by teacher | Yes | Yes | Yes | PDI | Derived
5 | Data & Trends | Trainings | Campus-wise training trends | Yes | Yes | No | PDI | Aggregated
6 | Data & Trends | Trainings | Block-wise training view | Yes | Yes | No | PDI | Aggregated
7 | Data & Trends | Trainings | In-service vs new joiners split | Yes | Yes | No | PDI | Computed
8 | Data & Trends | Trainings | Domain-wise (Academic / Specialist) | Yes | Yes | No | PDI | Derived
MODULE 2: DATA & TRENDS — GOALS
S.No | Module | Sub-Module | Feature | Admin | Leader | Teacher | Data Source | Logic | Status | Risk | Remarks
9 | Data & Trends | Goals | Individual goal listing | Yes | Yes | Yes | PDI | Static
10 | Data & Trends | Goals | Goal status (Not started / In progress / Achieved) | Yes | Yes | Yes | PDI | Derived
11 | Data & Trends | Goals | Goal progress % | Yes | Yes | Yes | PDI | Computed
12 | Data & Trends | Goals | School-level goals | Yes | Yes | No | PDI | Aggregated
13 | Data & Trends | Goals | Block-level goals | Yes | Yes | No | PDI | Aggregated
14 | Data & Trends | Goals | Goal vs outcome trend | Yes | Yes | No | PDI | Computed
MODULE 3: DATA & TRENDS — OBSERVATIONS
S.No | Module | Sub-Module | Feature | Admin | Leader | Teacher | Data Source | Logic | Status | Risk | Remarks
15 | Data & Trends | Observations | Observation count per cycle | Yes | Yes | No | Observations | Aggregated
16 | Data & Trends | Observations | Domain-wise observation trends | Yes | Yes | No | Observations | Aggregated
17 | Data & Trends | Observations | Teacher-wise observation history | Yes | Yes | Yes | Observations | Static
18 | Data & Trends | Observations | Observation feedback visibility | No | Yes | Yes | Observations | Static
19 | Data & Trends | Observations | Improvement trend over time | Yes | Yes | No | Observations | Computed
MODULE 4: DATA & TRENDS — ASSESSMENT
S.No | Module | Sub-Module | Feature | Admin | Leader | Teacher | Data Source | Logic | Status | Risk | Remarks
20 | Data & Trends | Assessment | Assessment score overview | Yes | Yes | No | Assessment | Static
21 | Data & Trends | Assessment | Rubric-wise score breakdown | Yes | Yes | No | Assessment | Aggregated
22 | Data & Trends | Assessment | Teacher assessment report | Yes | Yes | Yes | Assessment | Derived
23 | Data & Trends | Assessment | Cycle-wise comparison | Yes | Yes | No | Assessment | Computed
MODULE 5: DATA & TRENDS — SURVEYS
S.No | Module | Sub-Module | Feature | Admin | Leader | Teacher | Data Source | Logic | Status | Risk | Remarks
24 | Data & Trends | Surveys | Survey participation rate | Yes | Yes | No | Surveys | Aggregated
25 | Data & Trends | Surveys | Question-wise response analysis | Yes | Yes | No | Surveys | Aggregated
26 | Data & Trends | Surveys | Individual response history | Yes | Yes | Yes | Surveys | Static
27 | Data & Trends | Surveys | Survey vs improvement correlation | Yes | Yes | No | Surveys | Computed
MODULE 6: DATA & TRENDS — SELF-LEARNING & LEARNING EVENTS
S.No | Module | Sub-Module | Feature | Admin | Leader | Teacher | Data Source | Logic | Status | Risk | Remarks
28 | Data & Trends | Self-Learning | Course completion tracking | Yes | Yes | Yes | LMS | Derived
29 | Data & Trends | Self-Learning | Learning hours summary | Yes | Yes | Yes | LMS | Aggregated
30 | Data & Trends | Learning Events | Event participation | Yes | Yes | No | Events | Static
31 | Data & Trends | Learning Events | Event impact trend | Yes | Yes | No | Events | Computed
MODULE 7: DATA & TRENDS — OKR DASHBOARD
S.No | Module | Sub-Module | Feature | Admin | Leader | Teacher | Data Source | Logic | Status | Risk | Remarks
32 | Data & Trends | OKR Dashboard | Org / school OKRs | Yes | Yes | No | OKR | Static
33 | Data & Trends | OKR Dashboard | Individual OKR mapping | Yes | Yes | Yes | OKR | Derived
34 | Data & Trends | OKR Dashboard | Progress vs target | Yes | Yes | Yes | OKR | Computed
35 | Data & Trends | OKR Dashboard | Multi-cycle OKR trends | Yes | Yes | No | OKR | Computed

## Role Wise ChecK
TEACHER LOGIN — CHECKLIST
S.No | Module | Sub-Module | Feature | Visible | Editable | Data Correct | UX OK | Status | Remarks
1 | Data & Trends | Trainings | Completed trainings | Yes | No
2 | Data & Trends | Trainings | Upcoming trainings | Yes | No
3 | Data & Trends | Goals | Individual goals | Yes | Yes
4 | Data & Trends | Goals | Goal progress % | Yes | Yes
5 | Data & Trends | Observations | Observation feedback | Yes | No
6 | Data & Trends | Observations | Observation history | Yes | No
7 | Data & Trends | Assessment | Individual assessment report | Yes | No
8 | Data & Trends | Surveys | Survey response history | Yes | No
9 | Data & Trends | Self-Learning | Course completion | Yes | No
10 | Data & Trends | Learning Events | Event participation | Yes | No
11 | Data & Trends | OKR Dashboard | Individual OKRs | Yes | Yes
12 | Data & Trends | OKR Dashboard | OKR progress | Yes | No
LEADER / HOS / ACADEMIC COORDINATOR LOGIN
S.No | Module | Sub-Module | Feature | Visible | Editable | Data Correct | UX OK | Status | Remarks
1 | Data & Trends | Trainings | Team training completion | Yes | No
2 | Data & Trends | Trainings | Campus / block filters | Yes | No
3 | Data & Trends | Goals | Team goals overview | Yes | No
4 | Data & Trends | Goals | Goal vs outcome trend | Yes | No
5 | Data & Trends | Observations | Observation trends | Yes | No
6 | Data & Trends | Observations | Teacher-wise drilldown | Yes | No
7 | Data & Trends | Assessment | Rubric-wise analysis | Yes | No
8 | Data & Trends | Surveys | Survey analytics | Yes | No
9 | Data & Trends | Self-Learning | Learning hours summary | Yes | No
10 | Data & Trends | Learning Events | Event impact | Yes | No
11 | Data & Trends | OKR Dashboard | School / team OKRs | Yes | No
ADMIN LOGIN — CHECKLIST
S.No | Module | Sub-Module | Feature | Visible | Editable | Data Correct | UX OK | Status | Remarks
1 | Data & Trends | Trainings | All training data | Yes | No
2 | Data & Trends | Trainings | Domain / campus mapping | Yes | Yes
3 | Data & Trends | Goals | Goal definitions | Yes | Yes
4 | Data & Trends | Goals | Goal status overrides | Yes | Yes
5 | Data & Trends | Observations | Observation data access | Yes | No
6 | Data & Trends | Assessment | Assessment configuration | Yes | Yes
7 | Data & Trends | Surveys | Survey setup & data | Yes | Yes
8 | Data & Trends | Self-Learning | LMS data sync check | Yes | No
9 | Data & Trends | Learning Events | Event master data | Yes | Yes
10 | Data & Trends | OKR Dashboard | OKR master setup | Yes | Yes
11 | Data & Trends | OKR Dashboard | Org-level progress | Yes | No

## Signoff
DATA & TRENDS — SIGN-OFF TABLE
Module | Sub-Module | Total Features | Owner | Remarks
Data & Trends | Trainings | 8 | Product
Data & Trends | Goals | 6 | Product
Data & Trends | Observations | 5 | Academics
Data & Trends | Assessment | 4 | Academics
Data & Trends | Surveys | 4 | Product
Data & Trends | Self-Learning | 2 | Product
Data & Trends | Learning Events | 2 | Product
Data & Trends | OKR Dashboard | 4 | Leadership
Status values: Yes / Partial / No
Risk Level: Low / Medium / High
DATA & TRENDS - FEATURE-WISE SIGN-OFF
Module | Sub-Module | Feature | Status | Risk Level | Go / No-Go | Owner | Remarks
Data & Trends | Trainings | Completed trainings list |  |  |  | Product
Data & Trends | Trainings | Upcoming trainings |  |  |  | Product
Data & Trends | Trainings | Attendance tracking |  |  |  | Academics
Data & Trends | Trainings | Completion % by teacher |  |  |  | Product
Data & Trends | Trainings | Campus-wise trends |  |  |  | Product
Data & Trends | Trainings | Block-wise trends |  |  |  | Product
Data & Trends | Trainings | In-service vs new joiners |  |  |  | HR
Data & Trends | Trainings | Domain-wise split |  |  |  | Academics
Data & Trends | Goals | Individual goals view |  |  |  | Product
Data & Trends | Goals | Goal status tracking |  |  |  | Product
Data & Trends | Goals | Goal progress % |  |  |  | Product
Data & Trends | Goals | School-level goals |  |  |  | Leadership
Data & Trends | Goals | Block-level goals |  |  |  | Leadership
Data & Trends | Goals | Goal vs outcome trend |  |  |  | Academics
Data & Trends | Observations | Observation count per cycle |  |  |  | Academics
Data & Trends | Observations | Domain-wise trends |  |  |  | Academics
Data & Trends | Observations | Teacher observation history |  |  |  | Academics
Data & Trends | Observations | Feedback visibility |  |  |  | Academics
Data & Trends | Observations | Improvement trend |  |  |  | Product
Data & Trends | Assessment | Assessment overview |  |  |  | Academics
Data & Trends | Assessment | Rubric-wise analysis |  |  |  | Academics
Data & Trends | Assessment | Individual assessment report |  |  |  | Academics
Data & Trends | Assessment | Cycle comparison |  |  |  | Product
Data & Trends | Surveys | Participation rate |  |  |  | Product
Data & Trends | Surveys | Question-wise analysis |  |  |  | Product
Data & Trends | Surveys | Individual responses |  |  |  | Academics
Data & Trends | Surveys | Survey vs improvement trend |  |  |  | Product
Data & Trends | Self-Learning | Course completion |  |  |  | Product
Data & Trends | Self-Learning | Learning hours summary |  |  |  | Product
Data & Trends | Learning Events | Event participation |  |  |  | Product
Data & Trends | Learning Events | Event impact trend |  |  |  | Product
Data & Trends | OKR Dashboard | Org / school OKRs |  |  |  | Leadership
Data & Trends | OKR Dashboard | Individual OKRs |  |  |  | Leadership
Data & Trends | OKR Dashboard | Progress vs target |  |  |  | Product
Data & Trends | OKR Dashboard | Multi-cycle trends |  |  |  | Product